Project: Drones Against Malaria and Dengue
Student Engineer:	Don Kaluarachchi
Student ID:	n10496262
Supervisor:	Dr Felipe Gonzalez
Meeting Date, Time, & Method	Thursday, Weekly at 5.30pm
Face to face Meeting	Phone	Email	Teams/Zoom

Report on Progress
Agenda & Discussion	Clarify deliverables, assessment items and refine high level objectives
Key project activities completed and reported on this meeting.	Meetings will be held weekly (Tuesday’s with Narmilan and Thursday’s with Felipe and Narmilan)and the communication method used will be email / Literature analysis in progress and have found few more papers relevant to topic. / Use test images to build orthomosaic images / Stakeholders involved in this project are
Issues/concerns/questions remaining	Time frame for the project / Processing time between the multi-spectral capture and spraying / How to spray based on image / Processing: Software tools needed and instructions for the dji T10
Any risks identified (particularly HSE)	Going out into the field / Data storage. Safety of hardware
Ethical considerations	Bioagent/Chemicals used / Ingestion by plants and people and regulations currently in place.
Sustainability considerations	Not discussed

Next actions agreed
Action	Who?	By when?
Draft project plan	Don	Next week meeting
High level objectives for detection and spraying	Don	Next week meeting
Con-Ops diagram illustrating the process	Don	Next week meeting
HSE and risk assessment	Don and Narmilan	Next week meeting

---- END OF MEETING NOTES ----